## Test Plan
Field | Detail
Project Name | Manual Testing of E-Commerce Web Application
Prepared By | Amit Kumar
Role | Manual QA Engineer (Trainee)
Objective | To test the core functionalities of an e-commerce web application including user registration, login, product search, add to cart, checkout, and order placement.
In Scope | User Registration; Login/Logout; Product Listing & Search; Product Details; Add to Cart; Cart Update; Checkout; Order Confirmation; Cross-browser testing; UI & Usability checks
Out of Scope | Performance testing; Database testing; Backend APIs; Load testing; Actual payment gateway integration
Test Approach | Analyze requirements, create test scenarios and test cases, perform functional/UI/regression/cross-browser testing, log defects, re-test and regress, prepare summary report.
Entry Criteria | Requirements understood; Test environment ready; Test data prepared; Build is stable.
Exit Criteria | All test cases executed; All high severity defects closed or deferred; Test summary report completed; No major blockers.
Risks | Unclear requirements; Limited test data; Frequent UI changes.
Assumptions | Functional flows remain stable; Test environment is accessible; Browsers installed.
Deliverables | Test Plan; Test Scenarios; Test Cases; RTM; Bug Report Sheet; Test Summary Report